FOS Foundational Blueprint Working Session - January 22, 2026

| Attendees | AA: Anne Moroni, Arnaud Mathieu, Prem Vijayan, Angela Lorenzen, Scott Wiederhold, Thomas Cochran, Kevin Keyes OW: Andrew Medland, Chris DeBrusk, Daniel Rye, Jason Lombardo, Lindsay Grant, James Lefevre, Steven Piotrowski |
| --- | --- |
| Objectives | - Inform: Foundational Blueprint Progress Update - Inform: Data Strategy and Governance - Inform: FOS Decomm & TDEC MIPS/Resource Utilization Update |

| Decisions made / approved | Date reviewed |
| --- | --- |
| None | N/A |

| Action items | Owner | Date discussed | Target completion |
| --- | --- | --- | --- |
| - Ensure that product owners and product teams are fully engaged and aligned with the FB team to achieve the current timelines. And establish a list of contacts to reach out to when product teams have questions. | Lakshmi / Chai / OW | 1/22/2026 | 1/30/2026 |
| - Establish a comprehensive list of roles and responsibilities related to various aspects of data governance and present it to the broader team for review | OW / Chai | 1/22/2026 | 2/13/2026 |
| - Develop a common understanding on the data scope encompassed within NXOP, detailing its boundaries and implications | OW / Lakshmi | 1/22/2026 | 3/27/2026 |
| - Share sample FOS Decomm deliverables | Roger / OW | 1/22/2026 | 2/13/2026 |

Discussion notes

Foundational Blueprint Progress Update:

- FB remains green and we are making progress towards mitigating the two risks we discussed.

  - RFI and RFP – Low Risk – Received vendor responses. Procurement seeks to maintain strong negotiating position. Risk will impact timeline only if the workload deployments to production are delayed.

  - FXIP Timeline – Low Risk - Ops Hub has provided the data required and we will have a CR raised next week.

  - ACTION: Need to investigate concern about product resource alignment required to hit current timelines.

- FB needs to ensure full alignment between technology leadership and business Product Owner(s)

  - Leadership committed new ways of working will break down siloes and we need to ensure this happens

  - Chai and team own documentation for the new architecture

  - Materials are stored in the AA wiki and Effectual knowledge transfer is ongoing

  - Lakshmi and team are the primary contacts for future FXIP architecture questions

  - Need to define how Lakshmi and Carlos will partner once workloads are deployed to production. Suggest business teams own products and IT teams own integrations.

  - ACTION: OW to work with Lakshmi and Chai to document ownership and points of contact

    - For example: Who is the point of contact if a business product manager wants to understand architecture changes?

Data Strategy and Governance:

- Current data strategy imperatives

  - Need to define how NXOP data structures will align with vendor solution integrations

  - Need to define how to maintain both FOS and NXOP data structures in parallel without impeding future model objectives

  - Need to define how NXOP data structures align with enterprise data structures that serve operations not in scope for NXOP

  - Need to include data governance, data architecture, data models, and tool selections

- We need to consider not only the current data model but also future data models

  - How do we converge datasets required to inform better decision making?

    - For example: Crew planning data and Crew ops data

  - How will we adopt the new model while continuing to sustain existing processes and tools operating on the old?

- We need clear roles and responsibilities, clear ownership and scope definitions, and accountable people

  - Operations team owns the data domain, IT owns the physical data structures, and logical models are owned jointly

  - Todd Waller is responsible for the enterprise data strategy

  - Kevin is a senior manager for ops data strategy

  - Scott has been a key strategic partner in thinking through data models

  - Prem and team will support physical design approach

  - Need to determine which business stakeholders will be required to support (e.g. Analytics, Solvers, etc)

  - We are working to fill open resource requisitions for one L5 and two L4

    - Will need to identify target candidates and keep them warm while gaining funding approval

  - Need to define which resources contributing to this effort will require NXOP allocation

- Over the next quarter, we need to start defining scope for this significant piece of work that could span the next 18-months+

  - ACTION: Request OW support documenting situation, goals, approach, resource requirements, and leading practices before progressing to workshops

  - ACTION: Need a POV on what data scope is covered within NXOP

FOS Decomm:

- Remain on-track from prior update

- Team continues to validate milestone dates and will review deliverables to confirm completion

- FOS Decomm work will produce an achievable plan with associated milestones to ensure NXOP can begin processing

  - Teams working to deliver milestones dates by end of next week supported by data

  - We need an established timeline so we can assess progress against commitments, assemble the critical path, and understand impacts to other workstreams

    - This information is essential to assess schedule risk

  - When can we have a migration plan for TPS and LPS?

- ACTION: We will come back to this group in the start of Feb with example artifacts

TDEC:

- Working with IBM and DXC, objective is to avoid $10 million of spend into a new mainframe environment for NXOP testing

  - Team is working on ways to avoid that cost

- We increased MIPS in 2025, so less concern about capacity in TDEC

- TDEC is used for QA and pre-prod activities

  - NXOP testing would need to be coordinated closely to not impact existing TDEC use cases

  - For example: Flight schedules are loaded into TDEC for QA before being loaded into production.