## Sheet1
Epic | Story ID | Title | Env Scope | State | Owner | Start Date | End Date | Description & Key Tasks | DoD / Acceptance Criteria
AWS Platform & Network Foundation Readiness | E0‑01‑S1 | Provision EKS clusters (east & west) with pod identities | Non‑prod east & west |  |  |  |  | Create multi‑AZ EKS clusters for NXOP; configure CNI, autoscaler, ingress, network policies; enable IRSA; deploy sample NXOP microservice via CI/CD. | EKS clusters up in both regions; sample NXOP SpringBoot service deployed via CI/CD; pods assume IAM roles via IRSA; readiness and liveness probes pass consistently.
AWS Platform & Network Foundation Readiness | E0‑01‑S2 | Provision MSK clusters with IAM and OIDC auth | Non‑prod east & west |  |  |  |  | Create MSK clusters for NXOP; configure IAM auth for internal producers/consumers and OIDC client credentials for external clients; create NXOP topics (APIs, adapters, processors, connectors). | MSK clusters reachable from EKS pods using IAM auth; external test client connects via OIDC; all required topics created with documented naming and retention; test messages successfully produced and consumed in both regions.
AWS Platform & Network Foundation Readiness | E0‑01‑S3 | Configure MSK bi‑directional cross‑region replication | Non‑prod east & west |  |  |  |  | Implement east↔west replication between NXOP MSK clusters (MSK Replicator/Kafka Connect) for selected topics, including those feeding vendor systems, FXIP, OpsHub, and CCI‑related flows; test cross‑region behavior. | Cross‑region replication configured for relevant topics; simulated failover shows messages produced in either region appear in the other within SLA; no unacceptable duplication/order issues for idempotent consumers.
AWS Platform & Network Foundation Readiness | E0‑01‑S4 | Provision Global DocumentDB & validate MongoDB compatibility | Non‑prod shared |  |  |  |  | Provision Global DocumentDB (multi‑region) for NXOP; validate compatibility with FXIP MongoDB schemas and query patterns used by stateful services and Azure Table‑based metadata; validate TLS and region‑aware connectivity from EKS. | Global DocumentDB cluster running with automated backups and encryption; CRUD and query tests pass against primary and regional replicas; NXOP services connect from EKS using IRSA+Secrets Manager; documented client connection strategy for regional failover.
AWS Platform & Network Foundation Readiness | E0‑01‑S5 | Provision S3 buckets with MRAP for long‑term storage and lifecycle | Non‑prod shared |  |  |  |  | Create S3 buckets for NXOP long‑term storage; configure encryption, block public access, bucket policies, lifecycle rules; configure Multi‑Region Access Point (MRAP) for these buckets so they are globally accessible without explicit replication/failover; map Azure Blob containers from FXIP to S3 structure. | S3 buckets created with encryption and no public access; MRAP configured for relevant buckets; access to S3 via MRAP from both regions validated; lifecycle policies configured and validated with sample objects; Blob→S3 mapping documented and approved.
AWS Platform & Network Foundation Readiness | E0‑01‑S6 | Configure Route 53 zones & integrate with Akamai/InfoBlox | Non‑prod DNS |  |  |  |  | Design DNS for NXOP across Akamai GTM, Route 53, Azure Traffic Manager (for coexistence with FXIP), InfoBlox; configure hosted zones and health checks. | NXOP non‑prod endpoints resolvable externally and internally; health checks configured for EKS ingress; DNS resolution via Akamai, Route 53 and InfoBlox validated.
AWS Platform & Network Foundation Readiness | E0‑01‑S7 | Configure AWS ARC and SSM documents for failover | Non‑prod east & west |  |  |  |  | Implement ARC routing controls for NXOP east/west endpoints; create SSM documents for regional traffic failover; dry‑run failover between regions. | ARC routing controls deployed for relevant NXOP non‑prod endpoints; SSM documents successfully switch endpoints; RTO/RPO for regional failover measured and documented.
Data Migration & Synchronization Readiness | E0‑02‑S1 | Design data migration and sync strategy | Non‑prod |  |  |  |  | Define migration strategy from FXIP Confluent MongoDB to NXOP Global DocumentDB; Azure Tables→DocumentDB; Azure Blob→S3 (MRAP‑backed buckets); define full‑load and incremental sync; plan cut‑over (dual‑write/CDC/freeze window); define reconciliation and rollback strategy. | Migration design approved; all FXIP collections/tables/containers inventoried and classified; sequencing, downtime and rollback clearly defined; data owners sign off.
Data Migration & Synchronization Readiness | E0‑02‑S2 | Implement and test MongoDB → Global DocumentDB tooling | Non‑prod |  |  |  |  | Implement tooling to migrate FXIP MongoDB data into NXOP Global DocumentDB; run full load in non‑prod and validate schema mapping and transformations. | Full migration load completed in non‑prod; row counts and key metrics match within tolerance; migration window within plan.
Data Migration & Synchronization Readiness | E0‑02‑S3 | Implement Azure Tables & Blob → DocumentDB & S3 (MRAP) | Non‑prod |  |  |  |  | Migrate FXIP Azure Tables metadata into DocumentDB collections; move Blob objects representing documents into S3 buckets fronted by MRAP; validate metadata→S3 linkage using MRAP endpoints. | Non‑prod Azure Tables and Blob data fully migrated and validated; NXOP apps/admin tools retrieve documents correctly via DocumentDB metadata and S3 MRAP endpoints.
Data Migration & Synchronization Readiness | E0‑02‑S4 | Implement EventHub, MQ, MSK adapters/connectors | Non‑prod |  |  |  |  | Build and deploy adapters/connectors for NXOP: (1) EventHub→MSK connector (FXIP→NXOP); (2) MSK→EventHub (Kafka) adapter (NXOP→FXIP); (3) MSK→On‑Prem MQ adapter (NXOP→OpsHub); (4) On‑Prem MQ→MSK adapter (OpsHub→NXOP); define topics/queues, ordering, idempotency and error‑handling strategy. | All four adapter/connector paths operational in non‑prod; latency within SLAs; no data loss or unacceptable duplication; mapping of FXIP EventHub/MQ topics/queues to NXOP MSK topics documented.
Data Migration & Synchronization Readiness | E0‑02‑S5 | Implement data reconciliation framework | Non‑prod |  |  |  |  | Build reconciliation tooling comparing FXIP vs NXOP data for key entities (MongoDB vs Global DocumentDB, Azure Tables vs DocumentDB, Blob vs S3 MRAP buckets); define thresholds and exception processes. | Automated reconciliation available for critical datasets; exception thresholds and handling process agreed; data owners sign off.
Data Migration & Synchronization Readiness | E0‑02‑S6 | Dress rehearsal of data migration in non‑prod | Non‑prod |  |  |  |  | Execute end‑to‑end rehearsal: full load, delta sync, use of adapters/connectors (EventHub, MQ), cut‑over simulation, rollback simulation; capture timings and issues. | Rehearsal completed; all flows including FXIP integrations (EventHub, OpsHub MQ) use NXOP migration path; migration and rollback complete within planned windows; rehearsal report approved; production migration runbook updated.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S1 | Validate Direct Connect & on‑prem network paths | Non‑prod |  |  |  |  | Confirm Direct Connect routing from NXOP VPCs to on‑prem networks; validate IP ranges, firewalls, SGs, NACLs; test connectivity from EKS pods to all on‑prem endpoints used by NXOP microservices (including OpsHub MQ and other on‑prem APIs). | Connectivity validated to all on‑prem targets; traceroute/reachability analysis performed; connectivity matrix (IPs, ports, protocols, services) documented and agreed with network/security teams.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S2 | Validate connectivity to vendor systems (FlightKeys, CyberJet FMS, IBM Fusion Flight Tracking) | Non‑prod |  |  |  |  | For FlightKeys and CyberJet FMS: validate connectivity from NXOP EKS to vendor RabbitMQ brokers/queues; for IBM Fusion Flight Tracking: validate HTTPS API connectivity (DNS, TLS, IP allowlists); simulate vendor regional failover where supported (including Vienna DR endpoints as applicable). | All vendor RabbitMQ endpoints (FlightKeys, CyberJet FMS) reachable; NXOP test consumers can connect and read messages; IBM Fusion Flight Tracking APIs reachable and pass TLS/auth checks; vendor DR/failover scenarios behave as expected.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S3 | Validate Apigee microgateway routing to NXOP APIs (including CCI integration) | Non‑prod |  |  |  |  | Configure Apigee microgateways to route traffic to NXOP APIs in non‑prod; validate authentication flows, contracts, headers, and error codes; ensure FXIP consumers and the Crew Check In (CCI) system can call NXOP APIs via Apigee without contract breaks. | All 7 NXOP APIs reachable via Apigee; regression tests for internal consumers, external consumers, and CCI integration pass; no breaking changes to external API contracts.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S4 | Validate internal‑only endpoints & IP allowlists | Non‑prod |  |  |  |  | Ensure internal NXOP endpoints resolve to internal IPs via InfoBlox/Route 53; confirm internal IP allowlists updated for all internal consumers and systems (including FXIP components, CCI, OpsHub, and other internal apps). | Internal endpoints resolvable to correct internal IPs; access tests from expected internal consumers (FXIP, CCI, OpsHub‑connected services) succeed; IP allowlist updates approved by Security and Network.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S5 | Validate NXOP data adapters (Azure/on‑prem → vendor RabbitMQ and IBM APIs) | Non‑prod |  |  |  |  | Deploy NXOP data adapter microservices in EKS non‑prod; validate flows: Azure/FXIP/on‑prem sources → adapters → vendor RabbitMQ queues (FlightKeys, CyberJet FMS) and IBM Fusion Flight Tracking APIs; verify payload transformations and routing logic. | All adapters function correctly in non‑prod; end‑to‑end test cases from source systems through adapters to vendor RabbitMQ queues/APIs pass; behavior equivalent or improved over FXIP implementation.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S6 | Validate NXOP data processors (vendor RabbitMQ/APIs → MSK) | Non‑prod |  |  |  |  | Deploy NXOP data processor microservices in EKS non‑prod; validate that processors consume from FlightKeys and CyberJet FMS RabbitMQ queues and IBM Fusion APIs and publish transformed messages to appropriate NXOP MSK topics. | All processors read vendor RabbitMQ queues and IBM Fusion APIs correctly and publish to MSK topics; payloads validated against schemas; retry/backoff and error handling behaviors tested.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S7 | Validate microservices with on‑prem API and MQ integrations (OpsHub, others) | Non‑prod |  |  |  |  | For NXOP microservices that call on‑prem APIs or integrate via OpsHub MQ, validate DNS, TLS/mTLS (if applicable), authentication, MQ channel config, timeouts, retries, and error handling; ensure only authorized NXOP services can reach these endpoints. | All such NXOP services can reach on‑prem APIs and OpsHub MQ; timeouts, retries and circuit breakers work as designed; failures are observable in logs/metrics; access restricted by network policies and IAM.
Connectivity and Integration to Vendors, FXIP, OpsHub & On‑Prem Readiness | E0‑03‑S8 | Validate NXOP→FXIP EventHub integration for downstream FXIP consumers | Non‑prod |  |  |  |  | Validate that NXOP feeds FXIP Azure EventHub via the MSK→EventHub adapter; confirm that FXIP applications consuming from EventHub (including FXIP components and downstream systems) continue to function as expected while NXOP is the source. | MSK→EventHub adapter functioning; FXIP EventHub consumers receive correct messages from NXOP; no functional regression for FXIP downstream consumers; mapping of NXOP topics to FXIP EventHub topics documented.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S1 | Implement pod identities (IRSA) for all NXOP services | Non‑prod |  |  |  |  | Map each NXOP microservice and admin tool to IAM roles via IRSA; define least‑privilege policies for MSK, Global DocumentDB, S3 (MRAP), Secrets Manager, CloudWatch; remove static credentials from configuration. | All NXOP services in non‑prod use IRSA; no hard‑coded secrets; IAM policies reviewed and approved by Security; automated tests confirm least‑privilege access.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S2 | Implement Vault → AWS Secrets Manager replication | Non‑prod |  |  |  |  | Design and configure secure replication of secrets from Hashicorp Vault into AWS Secrets Manager for NXOP; define naming and rotation policies; monitor sync. | All required NXOP secrets present in Secrets Manager; sync process monitored with alerts; procedures for updating secrets in Vault and verifying propagation documented.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S3 | Update NXOP services to use AWS Secrets Manager | Non‑prod |  |  |  |  | Refactor NXOP service configuration so all secrets are retrieved from Secrets Manager via IRSA; ensure secrets are not embedded in images or plain‑text configs; validate runtime secret access. | All NXOP services in non‑prod retrieve secrets exclusively from Secrets Manager; no secrets in container images or unencrypted configs; secret rotation test executed successfully.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S4 | SSL/TLS certificate management in ACM and vendor PKI | Non‑prod |  |  |  |  | Manage TLS certificates for NXOP external APIs, vendor connections, internal tools via ACM and vendor CA; ensure trust chains between AWS workloads and on‑prem/vendor systems; attach ACM certs to NXOP ingress and load balancers. | All NXOP HTTPS endpoints use valid certificates; TLS handshake tests pass from FXIP, vendors, CCI, OpsHub; certificate inventory and renewal process documented and monitored.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S5 | Validate Ping Identity + Entra ID access to NXOP tools | Non‑prod |  |  |  |  | Integrate SSO into NXOP admin web UI and AWS‑hosted operational tools via Ping Identity and Entra ID; implement RBAC and test. | NXOP admin UI and tools accessible via SSO; RBAC enforced; security/pen‑test of SSO and RBAC passed or mitigations agreed.
Security, Identity, Secrets & Certificates Readiness | E0‑04‑S6 | Validate IP allowlists and firewall rules | Non‑prod |  |  |  |  | Compile IP ranges/endpoints for vendors (FlightKeys, CyberJet FMS, IBM Fusion), FXIP, CCI, OpsHub, and admin access; ensure firewalls and IP allowlists updated for NXOP egress and ingress. | All critical flows (vendor, FXIP, CCI, OpsHub) succeed from NXOP; no unnecessary open ingress/egress; Security and Network sign‑off obtained.
Observability, Monitoring, Logging & Alerting Readiness | E0‑05‑S1 | Configure Mezmo logging for NXOP workloads | Non‑prod |  |  |  |  | Configure log shipping from NXOP EKS (Fluent Bit/Fluentd/sidecars) to Mezmo; standardize log formats, correlation IDs, log levels across NXOP microservices, adapters, processors, and connectors. | Logs from all NXOP non‑prod microservices and admin tools appear in Mezmo; end‑to‑end transaction tracing possible using correlation IDs; logging standards documented and adopted.
Observability, Monitoring, Logging & Alerting Readiness | E0‑05‑S2 | Configure Dynatrace for NXOP (EKS, MSK, Global DocumentDB) | Non‑prod |  |  |  |  | Deploy Dynatrace agents/operator for NXOP EKS clusters; integrate MSK and Global DocumentDB metrics; instrument key NXOP Java/SpringBoot transactions (including vendor, FXIP, CCI, OpsHub flows). | All NXOP services visible in Dynatrace; service maps available; dashboards for EKS, MSK, DocumentDB created; baseline performance metrics captured.
Observability, Monitoring, Logging & Alerting Readiness | E0‑05‑S3 | Configure CloudWatch dashboards and alarms | Non‑prod |  |  |  |  | Create NXOP CloudWatch dashboards for EKS nodes, MSK brokers, DocumentDB instances/replicas, S3 MRAP endpoints, network; configure alarms for critical metrics (CPU, memory, latency, error rate, disk, queue depth, replication lag). | Dashboards implemented and documented; alarms defined and successfully tested; integration to PagerDuty confirmed.
Observability, Monitoring, Logging & Alerting Readiness | E0‑05‑S4 | Integrate PagerDuty with NXOP monitoring | Non‑prod |  |  |  |  | Configure PagerDuty services and escalation policies for NXOP; integrate CloudWatch and Dynatrace alerts; define on‑call rota. | Test incidents from NXOP non‑prod generate PagerDuty alerts and follow correct escalation; on‑call rota documented; no misrouted alerts.
Observability, Monitoring, Logging & Alerting Readiness | E0‑05‑S5 | Define and validate SLOs/SLIs for critical NXOP flows | Non‑prod |  |  |  |  | Define SLIs and SLOs for critical NXOP flows: vendor data (RabbitMQ, IBM Fusion APIs), FXIP EventHub/MQ flows, CCI API integration, OpsHub MQ flows; implement SLO dashboards and alerts. | SLOs/SLA targets agreed with business; SLO dashboards implemented; SLO breach warnings and alerts tested for key NXOP flows.
Non‑Prod Functional, Performance, Chaos & DR Testing Readiness | E0‑06‑S1 | End‑to‑end functional regression | Non‑prod |  |  |  |  | Execute full regression across 21 NXOP microservices (APIs, adapters, processors, integration services) and 6 admin tools; cover vendor flows (FlightKeys, CyberJet FMS, IBM Fusion), FXIP EventHub feeds, OpsHub MQ adapters, and CCI API integration. | 100% of agreed regression executed; all critical/high defects resolved or explicitly accepted with mitigation; business and QA sign off NXOP functional readiness.
Non‑Prod Functional, Performance, Chaos & DR Testing Readiness | E0‑06‑S2 | Performance and scalability testing | Non‑prod (perf env) |  |  |  |  | Define workload models for NXOP typical and peak loads across critical flows (vendor queues/APIs, FXIP EventHub/MQ, CCI); execute performance tests; validate autoscaling of EKS, MSK, Global DocumentDB. | NXOP meets throughput and latency targets under peak load; no critical bottlenecks; autoscaling policies validated and tuned.
Non‑Prod Functional, Performance, Chaos & DR Testing Readiness | E0‑06‑S3 | Chaos and resilience testing | Non‑prod |  |  |  |  | Inject failures impacting NXOP: EKS node/pod crashes, MSK broker failures, Global DocumentDB node/region failover, vendor unavailability (RabbitMQ and APIs), FXIP EventHub connectivity issues, OpsHub MQ connectivity; validate NXOP self‑healing and fallback behavior. | For each injected failure, NXOP recovers within agreed RTO; no data loss beyond agreed RPO; resiliency gaps documented with remediation plans.
Non‑Prod Functional, Performance, Chaos & DR Testing Readiness | E0‑06‑S4 | DR and regional failover testing (ARC, MSK, Global DocumentDB) | Non‑prod east/west |  |  |  |  | Execute DR tests switching NXOP traffic between AWS east and west via ARC+SSM; validate MSK cross‑region replication under failover; validate Global DocumentDB regional failover (planned and unplanned), including client reconnection and impact on vendor/FXIP/CCI/OpsHub flows. Note: S3 uses MRAP and does not require explicit replication/failover, only connectivity verification. | DR tests executed with pre/post metrics; MSK replication continues to meet RPO; Global DocumentDB failover causes no data loss beyond RPO; NXOP applications reconnect correctly; RTO/RPO measured and documented; DR Runbook updated.
Non‑Prod Functional, Performance, Chaos & DR Testing Readiness | E0‑06‑S5 | Cut‑over simulation for FXIP migration Phases 1–3 | Non‑prod |  |  |  |  | Rehearse Phase 1–3 for NXOP in non‑prod: DNS and routing changes, EventHub↔MSK and MQ↔MSK adapter direction changes, publisher coordination table updates, FXIP and CCI endpoint shifts; test rollback for each scenario. | Full simulated cut‑over and rollback for each phase executed successfully; steps, timings, pre‑requisites, and responsibilities documented in cut‑over runbooks and RACI; scenarios include FXIP, CCI, OpsHub, and vendor integrations.