## Slide 1
FOS Sunset – Foundational Blueprint
Architecture Update
January 22, 2026

## Slide 2: Agenda
1 | Inform: Foundational Blueprint Progress Update
2 | Inform: Data Strategy and Governance
3 | Inform: FOS Decomm & TDEC MIPS/Resource Utilization Update
Confidential

## Slide 3
Foundational Blueprint Progress Update
1

## Slide 4: Foundational blueprint workstream: recent progress and risks Overall workstream status continues to be green; Production environment, initial systems integration framework, and app migration framework were delivered during the second half of December; There remains risks associated with FXIP development/testing and the cloud provider RFI timelines
Progress since December:
A
B
Developed initial first mover systems integration framework to inform Procurement's contracting structures on Dec 18., with validation from Business and IT leads
D
Continued development of ASM by deploying Flink jobs in the development environment on Dec. 30
Confidential
C
Developed initial application migration framework on Dec. 18
A
Timeline associated with cloud provider RFI / RFP: Current projected timeline for deployment of the initial NXOP production environment (3/31) could occur before cloud service provider evaluation process is complete
Risks:
completion of significant deliverable
E
Matured FXIP phased cutover plans to ensure preparedness for transition to NXOP on Jan. 6 and Jan. 15
B
Timeline FXIP development: Testing for FXIP is experiencing delays due to lacking connectivity with Ops Hub and automation script adjustments, which could delay go-live of NXOP’s initiation integration layer (i.e., FXIP)
Completed and documented the NXOP production environment on Dec 30

## Slide 5: Foundational blueprint workstream upcoming milestones Development of the FXIP in non-prod is delayed due to internal/external dependencies, with timelines pending clarification by 1/23; All other workstream milestones are on track
 | Upcoming milestone | Target date | Status | Notes
 | Develop NXOP integration layer (FXIP) in non-prod | Jan. 9 | Delayed | Working with the OpsHub team to establish connectivity for critical data required in NXOP for FXIP
 | Full non-prod environment ready | Jan. 21 | Complete | Demo and handover session of the non-production environment done on 1/21
 | Develop ASM GraphQL services in dev | Jan. 30 | On track | AA networking team is developing infrastructure to connect with FAA data feeds to prevent delays
 | Develops FinOps strategy | Feb. 13 | On track | No blockers; AA FinOps team has been engaged
 | Identify Crew Pay data dependencies | Feb. 20 | On track | No blockers; Initial discovery sessions have started
 | Push FXIP to prod | Mar. 2 | On track | No blockers; prod go-live timelines include a cushion for development delays
 | Push ASM to prod | Mar. 2 | On track | No blockers; prod go-live timelines include a cushion for development delays
A
B
C
D
E
F
Confidential
G

## Slide 6
Data strategy and governance
2

## Slide 7: NXOP Data Strategy & Governance How are we approaching data strategy, governance, and modelling standards to ensure alignment between NXOP, legacy platforms, new applications, and vended solutions?
Confidential
Draft
Discussion Topics (not exhaustive)
Who will be accountable for defining NXOP data strategy, governance, ownership, data quality, and other foundational principles ?
Who will be accountable for defining the business data model, data catalogue and metadata management, and technical stewardship?
How will vendor solution data structures influence NXOP?
How will NXOP standards align with broader enterprise data strategy?
What is the approach to ensuring NXOP accommodates legacy data models while enabling innovation and improvement?
What guiding principles and standards will inform NXOP data impacts to downstream systems? Who is responsible for ensuring compliance?
What are the business/functional requirements for data (e.g., historical data retention, snapshots, privacy and regulatory compliance, data residency, data lineage tracking, etc.)?
What are the non-functional requirements (e.g., security controls, compliance controls, latency, availability, velocity, etc.) that need to be adhered to?
Who is responsible for ensuring data standards compliance (E.g. Transactional workloads, day-of optimizers, long-term analytics)?
How should “data products” be considered in the context of NXOP?
How do we ensure AI-readiness of NXOP data?
As FXIP prepares for its transition to a production environment, and data integration with the first AA systems is set to commence, it is imperative to formalize a data strategy and governance framework.
Now is the right time to revisit this discussion
The NXOP team discussed Data Management as a persistent theme during PI Planning
The systems implementation workstream has started to discuss data requests from the first movers
How do we want to proceed
Lakshmi Lanka, Kevin Keyes, and Oliver Wyman have agreed to coordinate multiple working sessions in the upcoming weeks to clarify current state and expand on existing methods and resource requirements
Are there other questions we need to answer?

## Slide 8: NXOP Data Model Strategy & Governance For discussion
Confidential
Draft
Build a governed, canonical domain data model as the single source of semantic truth for operations.
Use data contracts + schema registries + APIs to guarantee integration between legacy, new, and vendor systems.
Establish a formal data governance and product model (roles, workflows, standards) to guide intentional evolution.
Deliver this through an incremental program: design canonical model → implement interoperability layer (APIs, adapters) → migrate & validate → operate & evolve with metrics.
NXOP
Flights
Crew
?
?
Load
?
FOS
Legacy Solutions
Custom Solutions
Vendor Solutions
Legacy Integrations
Future Integrations
Legacy Integrations
OpsHub
Transformation
Layer

## Slide 9: Proposed data ownership The program must establish clear accountability by designating owners for each data area. This will enhance transparency, streamline decision-making, and promote collaboration, driving our objectives forward.
Confidential
Draft
Data area | Responsible Teams / Org | 
 | Option 1 – Align with enterprise tool set | Option 2 – Autonomous tool set
Data product | Ops planning & performance Airline operations technology | 
Data model | Ops planning & performance Airline operations technology | 
Data movement | Ops planning & performance Airline operations technology | 
Data lake pipeline | Data Engineering, Automation, & Analytics | Airline operations technology
Data lake infrastructure | Data Engineering, Automation, & Analytics | Airline operations technology

## Slide 10
FOS Decomm & TDEC MIPS/Resource Utilization Update
3

## Slide 11: Flight Milestones – Path to Green
Status | 
ID | Feature/Activity Title | Team | Target Date | Status | Risks | Dependencies | Comments
1 | Confirm and refine TPS/LPS discovery target dates | FOS | 1/23/26 | On track |  |  | Analysis to provide estimated discovery timeline in progress
2 | Identify dependencies on capabilities external to FOS (TPS) | OpsHub | 1/31/26 | On Track |  |  | Co-Pilot will be utilized​; Analysis in progress
3 | Identify dependencies on capabilities external to FOS (LPS) | OpsHub | 1/31/26 | On track |  |  | Co-Pilot will be utilized​; Analysis in progress
4 | Create migration strategy for TPS capability | FOS | 1/31/26 | On Track |  | Vendor selection* | Analysis in progress; may depend on vendor selection
5 | Create migration strategy for LPS capability | FOS | 2/28/26 | On Track |  | Vendor selection* | Dependent on vendor selection
6 | Identify dependencies on capabilities internal to FOS | FOS | 3/31/26* | On Track |  |  | Discovery underway; dates to be adjusted based on estimates provided 1/23
7 | Identify the data elements to patch back to FOS (TPS) | FOS | 3/31/26* | On Track |  | Vendor selection* | Will evolve as discovery of capabilities internal to FOS is completed.
8 | Identify the data elements to patch back to FOS (LPS) | FOS | 3/31/26* | On track |  | Vendor selection* | Will evolve as discovery of capabilities internal to FOS is completed.
* Indicates dates subject to change based on high-level estimates; Refined estimates targeted 1/23
Legend
Not started
On track
At risk
Delayed
Complete

## Slide 12: Crew Pay Milestones – Path to Green
Status | 
ID | Feature/Activity Title | Team | Target Date | Status | Risks | Dependencies | Comments
1 | Identify the data elements in FCRM | FOS | 12/19/25 | Complete |  |  | Completed on 12/17​
2 | Confirm and refine Crew Pay discovery target dates | FOS | 1/31/26 | On track |  |  | Commitment to provide refined dates by 1/31 as of 1/13
3 | Confirm and refine Crew Pay discovery target dates after vendor selection | FOS | TBD | Not started |  |  | 
4 | Identify the FOS source record of FCRM identified fields | FOS | 2/10/26* | On track |  |  | Kicked off identification as of 1/13
5 | Identify Crew Comp Excel macros | Crew Pay BU | 2/10/26* | On track |  |  | List of processes identified and gathering details.
6 | Identify 3rd party reports for Crew Comp | Crew Pay BU | 3/24/26* | Not Started |  |  | Dependent on other teams to provide info​
7 | Ops/Crew Hub & External Apps dependency plan | OpsHub / CrewHub | 3/31/26* | On track | FOS-09-00 – many teams that need to be consulted |  | Completed 2 of 3 sessions with Ops/Crew Hub consumers
8 | Identify Crew Comp mid-range apps impact | Crew Pay Mid-range | 4/7/26* | On track |  |  | Template to gather information is finalized. Kicked off as of 1/13
9 | Identify applications that have a dependency on FCRM | Crew Pay / DE | 4/7/26* | Not Started |  |  | 
10 | FOS displays/command catalog complete with disposition draft | FOS | 5/26/26* | Not Started |  |  | 
11 | Identify the data element gaps in Crew/Ops Hub and FCRM feed | OpsHub / CrewHub | 5/26/26* | Not Started |  |  | 
12 | Any impact to non-pay processes within FOS | FOS | 7/14/26* | Not Started |  |  | Pramod due diligence complete; Need DXC deep dive
13 | FOS Screen Scraping (external to Crew Comp) | FOS | 8/11/26* | Not Started |  |  | Smaller effort; dependent on other teams
* Indicates dates subject to change based on high-level estimates; Refined estimates targeted 1/31
Legend
Not started
On track
At risk
Delayed
Complete
Priority Note: Split Duties and FOS Decomm are both running in parallel; Team members from 3+ Squads will contribute to Crew Pay Discovery activities in Release 1.

## Slide 13: TDEC MIPS/Resource Utilization - update for reference Our ongoing approach is to focus on our two guiding principles: Be as non-disruptive as possible and avoid capital costs
Progress to date:
AA experts have engaged IBM and DXC in parallel to provide options to address our capacity risk and mitigate the need to invest approximately $10 million in funds to establish a new testing environment.
This week, the IBM engagement has resulted in the following approaches:
Proposed next steps:
The engagement with IBM will be compared to DXC log analysis and choose the best approach
  Options 2 is not aligned with the approach that AA is willing to consider
We will continue our parallel engagement with DXC, as we have been doing over the past months
  We will review DXC’s current monitoring process to ensure it achieves the same level of insight as Approach 1 from IBM
1 | Mainframe Capacity & MIPS Optimization – IBM will review the server logs to identify high usage areas in TDEC
2 | Leverage IBM’s AI tools to review the identified segments – Based on the results from Option 1, IBM will then use their AI tools to review the areas consuming the most resources and provide suggestions

## Slide 14
Appendix Material
A

## Slide 15: FOS Decomm Recent Progress
Crew Pay
Completed the identification of FCRM data elements
Finalized template to capture the Crew comp mid-range and BU owned excel macros
Kicked off identification of Crew Comp mid-range apps and the FOS source record of FCRM
PI planning complete on 1/14; priority & workload assigned to multiple squads dedicated to FOS discovery work
Completed all three working sessions with 90 potentially dependent product teams for the “Ops/Crew Hub & External Apps dependency plan” milestone
Continued to refine initial target dates for 11 Crew Pay milestones - on track for 1/31 validation
Flight
Identified 21 systems so far dependent on LPS data and held dependency analysis / working sessions on week of 1/12
  Engaged external owners dependent on LPS data, results utilized in requirements and migration planning
  TPS external dependencies are much more contained than LPS; continued analysis in progress for completion 1/31
Continued hands-on code analysis to determine full decommissioning and design for LPS & TPS
  Analysis/discovery includes TPF code review of all potentially impacted systems; discovery is in progress for ACARS, FOS Cargo, DECS, FIMI, OASIS, TPS, WSS, XP/XML
TPS / LPS Initial Migration Strategy document is complete; final review to be complete by 1/31
Continued to refine initial target dates for discovery – on track for 1/23 validation